## Authentication
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-AUTH-001 | Successful login with valid credentials | WORKING | Redirected to student dashboard | None | 2026-04-07 | Isaac Banda
TC-AUTH-002 | Login fails with invalid password | WORKING | Error message shown | None | 2026-04-07 | Isaac Banda
TC-AUTH-003 | Role-based redirect (tutor) | WORKING | Tutor dashboard displayed | None | 2026-04-07 | Isaac Banda
TC-AUTH-004 | Unauthenticated access blocked | BUG FOUND | Not redirected to login | User is able to view other role dashboard page when you change the role at the end of the URL | 2026-04-07 | Isaac Banda
TC-AUTH-005 | Only allow Email format | WORKING | Displayed error requesting for valid Email format | None | 2026-04-07 | Isaac Banda

## Allocation
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-ALLOC-001 | Single allocation | WORKING | Record created | NONE | 2026-04-07 | Isaac Banda
TC-ALLOC-002 | Reallocation | WORKING | Old deactivated, new created | NONE | 2026-04-07 | Isaac Banda
TC-ALLOC-003 | Bulk allocation | WORKING | 10 records created | NONE | 2026-04-07 | Isaac Banda
TC-ALLOC-004 | Exception report (no tutor) | WORKING | list of unallocated students displayed | NONE | 2026-04-07 | Isaac Banda

## Messaging
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-MSG-001 | Tutee sends message | WORKING | Message stored, notification sent | NONE | 2026-04-07 | Isaac Banda
TC-MSG-002 | Message marked as seen | WORKING | Is_seen updated | NONE | 2026-04-07 | Isaac Banda
TC-MSG-003 | Reply with attachment | WORKING | Reply stored with FK | NONE | 2026-04-07 | Isaac Banda
TC-MSG-004 | Notification emails contain no content | WORKING | mail contains only link | NONE | 2026-04-07 | Isaac Banda

## Meetings
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-MEET-001 | Schedule online meeting | Done | Record created, notifications sent | No Defect | 2026-04-07 | Lawrance Chiyimba
TC-MEET-002 | Schedule in-person meeting | Done | Record correct, link null | No Defect | 2026-04-07 | Lawrance Chiyimba
TC-MEET-003 | Upload recording | Done | File record created | The system does not provision of recording the meetings | 2026-04-07 | Lawrance Chiyimba

## File Upload
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-FILE-001 | Upload document | WORKING | File record created | Files can be uploaded successfully | 2026-04-07 | Lawrance Chiyimba
TC-FILE-002 | File size validation | RESOLVED | Validation error shown | No Upload limitation. E.g I can upload the file upto 10GB | 2026-04-07 | Lawrance Chiyimba

## Blogging
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-BLOG-001 | Create blog post | Done | Assumed: blog record created | No Defects | 2025-04-07 | Lawrance Chiyimba

## Dashboards
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-DASH-001 | Student dashboard summary | WORKING | Data displayed correctly | No defects |  | Lawrance Chiyimba
TC-DASH-002 | Tutor dashboard sort/filter | WORKING | List reorders correctly | No defects |  | Lawrance Chiyimba
TC-DASH-003 | Admin views dashboards | WORKING | Admin can access both views | No defects |  | Lawrance Chiyimba

## Reports
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-RPT-001 | Statistics report (7 days) | WORKING | Counts calculated correctly | NONE | 2026-04-07 | Gabriel Muyauka
TC-RPT-002 | Exception report (28 days) | WORKING | At-risk students identified | NONE | 2026-04-07 | Gabriel Muyauka

## Responsive Design
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-RESP-001 | Mobile usability | WORKING | Responsive layout renders correctly | NONE | 2026-04-07 | Gabriel Muyauka
TC-RESP-002 | PC usability | WORKING | Responsive layout renders correctly | NONE | 2026-04-07 | Gabriel Muyauka
TC-RESP-003 | Tablet usability | WORKING | Responsive layout renders correctly | NONE | 2026-04-07 | Gabriel Muyauka

## Security
Test Case | Description | Status | Actual Result | Defects/Notes | Date | Tester's Name
TC-SEC-001 | Data isolation between students | WORKING | 403 returned | NONE | 2026-04-07 | Gabriel Muyauka
TC-SEC-002 | Passwords stored hashed | WORKING | bcrypt hash stored | NONE | 2026-04-07 | Gabriel Muyauka

## Summary
Metric | Value
Total Test Cases | 30+
Executed | 0 (all pending)
Critical Priority Cases | Authentication, Allocation, Security – pending execution
Defects Logged | None yet (execution not started)
Next Step | Begin execution once system is deployed in test environment